## Issue Tracking
CloudGate Issues List |  |  |  | Gemalto CloudGate Issue Tracking
Number | Date Reported | Customer |  | Issue | OPTION INTERNAL COMMENTS | Resolution / Plan | GetWireless comments | Status | Priority
|  |  | 1 | There appears to be a menu option for Active GPS antenna. When we enable this, we would expect the antenna port to provide a 3 volt bias voltage on the center pin to support an active GPS antenna, however no voltage is detected. | Retest requested as per Resultion/Plan On prototypes it says 3.4, but on first commercial products it will say 3.8V | Franco requested GW retest this by activating active GPS in the GUI and then activating a LuvitRED script that uses GPS. As a comment: On prototypes the front plate says 3.4V, but on first commercial products it will say 3.8V as the Gemalto module provides 3.8V for the active GPS antenna. | 23/11/2016 GW to test | Under Test (GW) | Medium
|  |  | 2 | We loaded a LuvitRED script that was built for a customer sending GPGGA NMEA reports to the serial port (expansion card) of the CloudGate. We noticed that there are no Latitude and Longitude coordinates in the GPGGA NMEA report coming from the GPS module in LuvitRED. The NMEA reports that do appear to have valid Latitude and Longitude are GPRMC, GNGNS, and GPVTG. The NMEA reports that do not appear to have valid Latitude and Longitude are GPGSA, GNGSA, and GPGGA. This is deviation from the GPS reporting function of the GTM689W based CloudGate and will impact customers using GPS. | Martin to investigate | This is under investigation. Sent some comments on the item back to GetWireless on Friday (25/11) |  | Under Test (GW) | Medium
|  |  | 3 | We developed a LuvitRED configuration to report temperature, device information, and GPS coordinates in refrigeration vehicles using the Banner Modbus temperature sensor. Using this configuration with the Gemalto based CloudGate, the Latitude and Longitude are no longer included in the report. | Martin to investigate | This is under investigation. Sent some comments on the item back to GetWireless on Friday (25/11) |  | Under Test (GW) | Medium
|  |  | 4 | For the configuration above, when we are connected on AT&T, the IMEI reported in the data report is “990002186076533” which is correct. When we switch the carrier to Verizon, the IMEI reported in the data report is “0x0099000218607653” which is not the IMEI, but would be the MEID is the prefix of “0x00” was removed. | Jimmy has a fix for this item. Not sure when the release will happen. Next release target early next week (5-7/12). | Fix will be available on the next firmware release (2.70.0). |  | New firmware | Medium
|  |  | 5 | We first tested the Gemalto CloudGate on T-Mobile which uses APN “epc.tmobile.com”. The settings in the GUI were left with “override network settings” set to “No”, meaning we want the CloudGate to add the APN it deems appropriate for the SIM card, and then we switched the SIM card to an AT&T SIM. The APN the CloudGate used did not update to an applicable AT&T APN like we would have expected, but instead it stayed at “epc.tmobile.com” which is the APN for T-Mobile and would not connect to the AT&T network. When we changed the “override network settings” to “Yes”, and manually changed the APN to “isp.cingular”, then the CloudGate connected on AT&T without delay. | Response from Jimmy is not acceptable. It should not be needed to restore the device to factory settings everytime you switch the SIM card. It was not this way on the old device and should not be like this on this one. It seems to be the same on the CG 3G and the CG LTE since February. It still does not seem logical to not be able to get the APN if it is on the DB, before it was like that, but for some reason this was changed back in February. We will have a call on this tomorrow (01/12). Call with Thomas and Jimmy, we will try to include a solution on the next release of firmware (not 2.70.0, but the one after that one) | This is the same on both the current CG 3G (Gobi) and the CG LTE. There was no change compared to those devices. We will try to get to a solution for the release following the 2.70.0. Some testing will be needed from GetWireless and Option. |  | New firmware | Low
|  |  | 6 | The CloudGate seemed to experience a significant delay in connecting on T-Mobile when switching from Verizon. Sometimes this takes 5 minutes. This delay was not noticed when the CloudGate had a AT&T SIM in it, and we switched from Verizon to AT&T. | Jimmy requested a Teamviewer session. Franco to work on getting this setup. 28/11 TV ready for Jimmy. 29/11 Jimmy tested today and saw a delay of 2 minutes to find a signal. He will investigate. | Jimmy needs to have a teamviewer session to debug what is going on here. 28/11 Teamviewer ready for Jimmy. 29/11 Jimmy tested and saw a delay of 2 minutes when switching. He will investigate and see if there is any chance for improvement. |  | Under Test (OP) | Medium
|  |  | 7 | Release notes should be adapted to show the support of the CG0198 | 2.70.0 is going to be the first Gemalto firmware. | According to Thomas the next release will include the CG0198 too. There is no date for that release yet as we want to include as many fixes as possible. Release by second week of December (2.70.0). |  | New firmware | High
|  |  | 8 | CGU needs to be adapted to accept the new CG0198 | Thomas mentioned this will be in place in Decemeber. Next release target early next week (5-7/12). | Will be there in December probably the second week. We are still figuring out the date. |  | New firmware | High
|  |  | 9 | Connection Hunting is missing

## Sheet3
High | Open
Medium | Closed
Low | Under Investigation (OP)
Under Test (GW)
Under Test (OP)
New firmware